## Procurement
EtC Panel Roles & Responsibilities Pre-contract / Procurement stage | Principal | Principal's Legal Representative | Engineer to Contract (EtC) | Engineer's Representative (ER) | Project Manager | Quantity Surveyor (QS) | Lead Designer | Main Contractor
Scope of engagement items
General
6.2.1(a) – Adviser to the Principal |  |  | ●
Chair PCG meeting (either PM or EtC) |  |  | ● |  | ●
Review of project procurement strategy | □ |  | □ |  | ●
Form of contract selection | ● | □ | □ |  | □ | □
Development of contract special condition clauses | □ | ● | □ |  | □
Main Contractor RFP submission tag and clarification clearance ('Apples for Apples' analysis) |  |  | □ |  | ● | □
Review tenderer's programme |  |  | □ |  | ●
Insurances, bonds, liquidated damages. Review details in tenders |  |  | □ |  | ●
Prepare contract documents for signing | □ |  | □ |  | ● | □ |  | □
Review and input to project risk register | □ |  | □ |  | □ | □ | □
Attendance at PCG meetings including site visit/walkover | □ | □ | □ |  | □ | □ | □
Contract Award (formal letter) | ●
Review of tenderer's price submission/schedule of quantities (if available) | [5 empty] | ●
Contract document execution and distribution | ● | [6 empty] | ●
Develop and maintain project risk register |  |  |  |  | ●
Manage PCG meeting action closure |  |  |  |  | ●
Ensure stakeholders are informed of project activities | □ |  |  |  | ●
Health and safety
Contractor Safety in Design responsibility defined in Contract including transfer of responsibility | □ | □ | □ |  | ● |  | □
Ensure Principal & Consultant team review and identify site specific features, hazards, buildability/staging risks and transfer this information to the Contractor | ● |  | □ |  | ●
l Deliverable required and party/parties responsible (Select from cell dropdown)
o Party/parties required to input, assist and coordinate (Select □ from cell dropdown)
(To clear cell, select and delete)
l Deliverable required and party/parties responsible (Select ● from cell dropdown)
o Party/parties required to input, assist and coordinate (Select □ from cell dropdown)
(To clear cell, select and delete)

## Contract Administration
EtC Panel Roles & Responsibilities Contract administration and observation stage | Principal | Principal's Legal Representative | Engineer to Contract (EtC) | Engineer's Representative (ER) | Project Manager | Quantity Surveyor (QS) | Lead Designer | Main Contractor
Scope of engagement items
Contract administration
Non-delegable EtC duties
5.21.1 – Advance notification (of material issues and/or breach of statutory duty) | ● |  | ● | □ | □ | □ |  | ●
6.2.1(a) – Adviser to the Principal |  |  | ●
6.3.1 – Appointment of the Engineer's Representative | ● |  | ● | □
6.3.5 – Appointment of assistants to the Engineer's Representative |  |  | ● | □
6.3.3(b) – Issue of Practical Completion Certificate | □ |  | ● | □ | □ | □ | □ | □
6.3.3(b) – Issue of Final Completion Certificate | □ |  | ● | □ | □ | □ | □ | □
6.3.3(b) – Granting of extensions of time |  |  | ● | □ | □ |  | □
6.3.4(b) – Investigating and actioning contractor dissatisfaction with instruction or decision from the Engineer's Representative |  |  | ● | □
12.2 – Issue of Progress Payment Schedules | □ |  | ● | □ | □ | □ |  | □
12.5 – Issue of Final Payment Schedule | □ |  | ● | □ | □ | □ |  | □
13.2.1 – Engineer's review (of dispute or difference under 13.1.2) | □ |  | ● | □ | □ | □ | □
13.2.3 – Engagement of independent expert (if required) | ● |  | □ |  |  |  |  | □
13.2.4 – Engineer's formal decision (final and binding, and if not using an independent expert) | □ |  | ● | □ | □ | □ | □
Delegable EtC duties (may be delegated to the Engineer's Representative)
Assessment of entitlement to a Variation (or a matter treated as if it is a Variation) |  |  | ● | □
Assessment and approval of the Contract Programme |  |  | ●
Valuing of a Variation (assessment of quantum) |  |  | □ |  |  | ●
6.3.3(b) – Changing of the Drawings or Specifications | □ |  |  | ● | □ | □ | □ | □
Monitoring of construction progress against the contract programme |  |  |  | ● | □
Issue of Engineer's Instructions |  |  | □ | ●
Issue of Variation Orders (Confirmation variation price is accepted) |  |  |  | ●
Undertake construction observation and capture progress photos |  |  |  | ● | □
Management of RFIs and expedient turnaround of consultants CANs |  |  |  | ● | ● |  | □ | □
Manage the resolution of construction defects during delivery and in the Defects Liability Period |  |  |  | ● | ● |  | □ | □
Ensure the timely delivery of consultant documentation, eg PS4s, defect lists etc |  |  |  | ● | ● |  | □ | □
Ensure the timely and accurate delivery of contractor documentation including shop drawings, samples, commissioning plans, PS3s, O&M Manuals etc |  |  |  | ● | ● |  | □ | □
Ensure the receipt and accuracy of parent company guarantees, bonds, warranties and guarantees, insurance certificates etc where required |  |  |  | ● | ● |  | □ | □
Ensure the receipt of Quality Plans, or Quality Documentation, inclusive of ensuring appropriate records are being kept |  |  |  | ● | ●
Health and safety
Review and accept SSSP, or other required contract documents | □ | □ | ● | □ |  |  |  | □
Review contractor adherence to approved SSSP, EMP, and QMP documents. Undertake regular reviews of these documents to ensure they remain current |  |  | ● | □
Ensure monthly H&S site audits are occuring | □ |  | ● | □
Regular visits to site |  |  | ● | □
Ensure receipt of Contractor temporary works designs |  |  | ●
Ensure the receipt of a Traffic Management Plan (if applicable), inclusive of ensuring regular audits are occurring | □ |  | ● |  |  |  |  | □
Undertake and document a H&S observation while on site | □ |  | □ | □ | □ | □ | □ | □
Ensure respective PCBU roles and responsibilities are discussed and agreed at the pre-start meetings | □ |  | □ | ● | ● |  | □ | □
Ensure all PCBU parties participate in review & identification of unique site-specific features, hazards & risks including SID recommendations at project start up meeting | □ |  | □ | ● | ● | □ | □ | □
Other general duties
Attendance at Project Board/Steering Group and Project Control Group Meetings | ● |  | ● | ● | ● | ● | ● | □
5.21.2 – Attendance at Advance Notification Meeting | □ | □ | ● | ● | □ | □ | □ | ●
Chair PCG meeting (either PM or EtC) |  |  | ● |  | ●
Attendance at Commercial Meetings | □ |  | □ | ● | □ | ● |  | ●
Review and input to project risk register | □ |  | □ | □ | □ | □ | □
Attend a pre-start meeting with the Contractor | □ |  | □ | □ | □ | □ | □ | □
Technical support to the EtC/ER (via site observations/records) | □ |  |  |  | □ | □ | □
Develop and maintain project risk register |  |  |  |  | ●
Maintenance of project registers (eg variations, instructions, document transmittals, risk register etc) |  |  |  |  | ●
Manage PCG meeting action closure |  |  |  |  | ●
Ensure stakeholders are informed of project activities | □ |  |  |  | ●
Organise and minute a pre-start meeting with the Contractor |  |  |  |  | ●
Manage pre-start meeting action closure |  |  |  |  | ●
Chair site meeting |  |  |  |  | ●
Manage site meeting action closure |  |  |  |  | ●
Ensure adherence to the Project Communication Plan by all parties |  |  |  |  | ●
Prepare and issue a monthly project status report to the Principal |  |  |  |  | ●
Prepare a project closure report |  |  |  |  | ●
l Deliverable required and party/parties responsible (Select from cell dropdown)
o Party/parties required to input, assist and coordinate (Select □ from cell dropdown)
(To clear cell, select and delete)
l Deliverable required and party/parties responsible (Select ● from cell dropdown)
o Party/parties required to input, assist and coordinate (Select □ from cell dropdown)
(To clear cell, select and delete)